## Decisions Register
SCHEME DECISION REGISTER
PROJECT |  |  | UU AMP8 FRAMEWORK - DD&B
PROJECT CODE |  |  | 1002-001848 - UU DD&B FLASS LANE
Ref | Stage | Meeting No. | Date | Context / Background | Description of Decision (What / Why) | Basis of Decision | Decision Owner | Delivery Owner | Stakeholders |  | Record of Agreement (email, meeting, etc.) | Status | Design Freeze Impact | Programme Impact | Delay | Cost Impact | Impact Type | Efficiency Gained |  | Score |  | Ranking | Actions / Follow-ups
[6 empty] | Supporting Information | Accountable | Responsible | Parties Consulted |  |  |  |  | (Y / N) | (Days / Weeks) | (£ or Range) | [6 empty] | Actions | Due Date
DR-001 | Outline Design | 1 | 2026-05-12 | Initial site constraints identified limited available footprint for new storm tanks. Ground investigation indicates high groundwater levels and poor bearing capacity, increasing construction complexity and cost risk for large in-situ concrete tanks. | Adopt precast above-ground storm attenuation tanks instead of below-ground in-situ reinforced concrete tanks to reduce construction risk, improve programme certainty, and minimise excavation in poor ground conditions. | Basis of Decision: Optioneering study, ground investigation results, cost plan comparison, programme risk assessment. Supporting Information: GI Report Rev A, Cost Estimate (Option 1 vs Option 2), Design Risk Assessment, Buildability Workshop outputs. | United Utilities | Murphy | United Utilities | ARUP | Outline Design Review Meeting Minutes – 12/05/2026 | Approved | Pre-freeze | Yes | 0 weeks (programme risk reduced; approx. 2 weeks float improvement) | Additional £35k (about 300-400 design hours) increase in design effort due to alternative solution requiring revised layouts, multidisciplinary coordination, and supplier engagement; justified by improved buildability and reduced design risk | Positive | Improved constructability, reduced excavation, lower temporary works requirement, reduced groundwater management. | YES | 2 | 1 | 2 - Medium | 1. Develop preliminary layout and GA drawings for above-ground tanks 2. Confirm structural design approach with precast supplier 3. Update cost plan and programme 4. Update risk register and mitigation measures | 2026-06-19
Note on J14: Themis Kourtellas: Select from Drop down list only - Add in sheet 2 list other party/local authority involved
Note on K14: Themis Kourtellas: Select from Drop down list only - Add in sheet 2 list other party/local authority involved

## Data Sheet
YES | United Utilities | YES - Positively | N/A
NO | Main Contractor | Yes - Negatively | Negative Impact
| ARUP | No | Neutral
| Local Authority |  | Good
HBT
OTB
MAE