## Summary
Project ID | Originator | Doc Type | Role | Seq No | Date Sent | Sender | Recipient | Required Date | Subject | Reply Date | Notes | Status
1002-001847 | JMS | RFI |  | 0001 | 2026-03-17 | Ciaran Hoban | Conal Cunningham | 2026-03-24 | MAE RFI - Management Plans | 2026-04-20 | JMS-MAE-RFI-000001 | Closed
1002-001847 | JMS | RFI |  | 0002 | 2026-03-19 | Ciaran Hoban | Conal Cunningham | 2026-03-26 | MAE RFI - Topo Data/Scan for Schneider Road |  | JMS-MAE-RFI-000002 | Open
1002-001847 | JMS | RFI |  | 0003 | 2026-03-19 | Ciaran Hoban | Conal Cunningham | 2026-03-26 | MAE RFI - Missing Existing Services Depths | 2026-03-26 | JMS-MAE-RFI-000003 | Closed
1002-001847 | JMS | RFI |  | 0004 | 2026-03-19 | Ciaran Hoban | Conal Cunningham | 2026-03-26 | MAE RFI - OSGB Laser Scan Tally Ho Site | 2026-03-24 | JMS-MAE-RFI-000004 | Closed
1002-001847 | JMS | RFI |  | 0005 | 2026-03-19 | Ciaran Hoban | Conal Cunningham | 2026-03-26 | MAE RFI - OSGB Georeferenced GPRS Tally Ho | 2026-03-24 | JMS-MAE-RFI-000005 | Closed
1002-001847 | JMS | RFI |  | 0006 | 2026-03-19 | Ciaran Hoban | Conal Cunningham | 2026-03-26 | MAE RFI - OSGB Georeferenced GPRS Schneider Road | 2026-03-26 | JMS-MAE-RFI-000006 | Closed
1002-001847 | JMS | RFI |  | 0007 | 2026-03-27 | Ciaran Hoban | Conal Cunningham | 2026-04-03 | MAE RFI - Trial Pits on Rising Main Diversion |  | JMS-MAE-RFI-000007 | Open
1002-001847 | JMS | RFI |  | 0008 | 2026-03-27 | Ciaran Hoban | Conal Cunningham | 2026-04-03 | MAE RFI - Temporary Overflow Diversion Solution & Sketch | 2026-04-01 | JMS-MAE-RFI-000008 | Closed
1002-001847 | JMS | RFI |  | 0009 | 2026-04-01 | Carys O'shea | Conal Cunningham | 2026-04-07 | Existing 900mm pipe within the screen chamber |  | JMS-MAE-RFI-000009 | Open
1002-001847 | JMS | RFI |  | 0010 | 2026-04-08 | Ciaran Hoban | Conal Cunningham | 2026-04-15 | MAE RFI - Rising Main Surveys Details & Coordinates |  | JMS-MAE-RFI-000010 | Open
1002-001847 | JMS | RFI |  | 0011 | 2026-04-08 | Ciaran Hoban | Conal Cunningham | 2026-04-15 | MAE RFI - Existing Screening Chamber Details (Tally Ho) | 2026-04-23 | JMS-MAE-RFI-000011 | Closed
1002-001847 | JMS | RFI |  | 0012 | 2026-04-08 | Ciaran Hoban | Conal Cunningham | 2026-04-15 | MAE RFI - Benching Arrangement Survey in Existing Screening Chamber (Tally Ho) |  | JMS-MAE-RFI-000012 | Open
1002-001847 | JMS | RFI |  | 0013 | 2026-04-08 | Ciaran Hoban | Conal Cunningham | 2026-04-15 | MAE RFI - Details of MH7515 and MH7506 |  | JMS-MAE-RFI-000013 | Open
1002-001847 | JMS | RFI |  | 0014 | 2026-04-09 | Ciaran Hoban | Conal Cunningham | 2026-04-16 | MAE RFI - Naming Conventions/Protocols | 2026-04-16 | JMS-MAE-RFI-000014 | Closed
1002-001847 | JMS | RFI |  | 0015 | 2026-04-21 | Ciaran Hoban | Conal Cunningham | 2026-04-28 | MAE RFI - Pumps in Existing Screening Chamber Information | 2026-04-23 | JMS-MAE-RFI-000015 | Closed
1002-001847 | JMS | RFI |  | 0016 | 2026-04-21 | Ciaran Hoban | Conal Cunningham | 2026-04-28 | MAE RFI - Existing Gasholder Location | 2026-04-22 | JMS-MAE-RFI-000016 | Closed
1002-001847 | JMS | RFI |  | 0017 | 17/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-03-24 | MAE TQ - Arrangement of Breaking into Existing Manhole (Schneider Road) |  | JMS-MAE-TQ-000001 | Open
1002-001847 | JMS | TQ |  | 0018 | 17/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-03-24 | MAE TQ - Arrangement from Screening Chamber to Shaft | 2026-03-24 | JMS-MAE-TQ-000002 | Closed
1002-001847 | JMS | TQ |  | 0019 | 17/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-03-24 | MAE TQ - 900NB Overfow Diversion | 2026-03-24 | JMS-MAE-TQ-000003 | Closed
1002-001847 | JMS | TQ |  | 0020 | 17/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-03-24 | MAE TQ - Precast Manhole Rings Supplier | 2026-03-24 | JMS-MAE-TQ-000004 | Closed
1002-001847 | JMS | TQ |  | 0021 | 17/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-03-24 | MAE TQ - Decommissioning Requirements |  | JMS-MAE-TQ-000005 | Open
1002-001847 | JMS | TQ |  | 0022 | 25/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-01 | MAE TQ - Confirm Outline Design Solution for MH01 (Tally Ho) | 2026-04-01 | JMS-MAE-TQ-000006 | Closed
1002-001847 | JMS | TQ |  | 0023 | 25/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-01 | MAE TQ - Confirm Outline Design Solution for MH02 (Tally Ho) |  | JMS-MAE-TQ-000007 | Open
1002-001847 | JMS | TQ |  | 0024 | 25/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-01 | MAE TQ - Confirm Outline Design Solution for MH03 (Tally Ho) |  | JMS-MAE-TQ-000008 | Open
1002-001847 | JMS | TQ |  | 0025 | 25/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-01 | MAE TQ - Confirm Outline Design Solution for MH04 (Tally Ho) |  | JMS-MAE-TQ-000009 | Open
1002-001847 | JMS | TQ |  | 0026 | 27/03/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-03 | MAE TQ - Buried Services Risk |  | JMS-MAE-TQ-000010 | Open
1002-001847 | JMS | TQ |  | 0027 | 01/04/2026 | Carys O'shea | Conal Cunningham | 2026-04-08 | T-connection setting out from proposed 1500mm dia. pipe from existing chamber to shaft. |  | JMS-MAE-TQ-000011 | Open
1002-001847 | JMS | TQ |  | 0028 | 01/04/2026 | Carys O'shea | Conal Cunningham | 2026-04-07 | Proposed rising mains connection to existing |  | JMS-MAE-TQ-000012 | Open
1002-001847 | JMS | TQ |  | 0029 | 01/04/2026 | Carys O'shea | Conal Cunningham | 2026-04-08 | Temporary MH in location on MH02 (for temporary phase) |  | JMS-MAE-TQ-000013 | Open
1002-001847 | JMS | TQ |  | 0030 | 08/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-15 | MAE TQ - Rising Main Diversion Supports & Pressure | 2026-04-22 | JMS-MAE-TQ-000014 | Closed
1002-001847 | JMS | TQ |  | 0031 | 08/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-15 | MAE TQ - Details of Opening at Existing Screening Chamber (Tally Ho) |  | JMS-MAE-TQ-000015 | Open
1002-001847 | JMS | TQ |  | 0032 | 08/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-15 | MAE TQ - Confirmation of Pumped Main from Flowmeter Chamber to MH03` |  | JMS-MAE-TQ-000016 | Open
1002-001847 | JMS | TQ |  | 0033 | 09/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-16 | MAE TQ - Trunk Main on Schneider Road GA |  | JMS-MAE-TQ-000017 | Open
1002-001847 | JMS | TQ |  | 0034 | 09/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-16 | MAE TQ - Confirm Outline Design Solution for MH01 (Schneider Road) |  | JMS-MAE-TQ-000018 | Open
1002-001847 | JMS | TQ |  | 0035 | 09/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-16 | MAE TQ - Confirm Outline Design Solution for MH02 (Schneider Road) |  | JMS-MAE-TQ-000019 | Open
1002-001847 | JMS | TQ |  | 0036 | 09/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-16 | MAE TQ - Confirm Outline Design Solution for MH03 (Schneider Road) |  | JMS-MAE-TQ-000020 | Open
1002-001847 | JMS | TQ |  | 0037 | 09/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-16 | MAE TQ - Confirm Outline Design Solution for MH04 (Schneider Road) |  | JMS-MAE-TQ-000021 | Open
1002-001847 | JMS | TQ |  | 0038 | 09/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-16 | MAE TQ - Confirm Outline Design Solution for MH05 (Schneider Road) |  | JMS-MAE-TQ-000022 | Open
1002-001847 | JMS | TQ |  | 0039 | 10/04/2026 | Ciaran Hoban | Conal Cunningham | 2026-04-17 | MAE TQ - Diversion/Disconnection of Electrical Services by Screening Chamber (Tally Ho) | 2026-04-24 | JMS-MAE-TQ-000023 | Closed
Formulas:
Required Date = SUM([Date Sent]+7)